## Sheet1
Unique ID | User Stories | Particulars (Today's work- Date to be mentioned) | Assignee | Reporter (Scrum Master) | Present / Absent | Status | Resolution | Created | Due | Fix Version/s | Product Backlog
1 | Create Git Repositry | adding all members and checking the clone for all the members | Eskala Srekar | Ajith Pai | Present | completed | resolved | 2020-01-16 | 2020-01-17 | N/A | leave this column as of now.
2 | Module workflow | making the workflow plan for the entire project | Ajith Pai | Ajith Pai | Present | completed | resolved | 2020-01-17 | 2020-01-17 | N/A
3 | Database Design | Design and correction of the database to be used for the project | Ajith Pai | Ajith Pai | Present | completed | resolved | 2020-01-18 | 2020-01-19 | N/A
4 | Idea Finalising | Finalising the whole project implementation. | Eskala Srekar | Ajith Pai | Present | completed | resolved | 2020-01-18 | 2020-01-19 | N/A
5 | Firebase account | making the firebase hosting account | Ajith Pai | Ajith Pai | Present | completed | resolved | 2020-01-20 | 2020-01-21 | N/A
6 | Create online url | Making the url id and deploy hello world | Ajith Pai | Ajith Pai | Present | completed | resolved | 2020-01-22 | 2020-01-23 | N/A
7 | SRS document Completion | to make the SRS document for the project | Kamal Kandula | Ajith Pai | Present | completed | resolved | 2020-01-23 | 2020-01-28 | 1.1
8 | SRS document Correction | All the errors, unrelated details and mistakes are corrected | Ajith Pai | Ajith Pai | Present | completed | resolved | 2020-01-28 | 2020-01-30 | 1.2
9 | Login mangament with OTP | The login management is made with Firebase | Ajith Pai | Ajith Pai | Present | completed | resolved | 2020-01-30 | 2020-02-03 | 1.1
10 | login test | testing the login | Prem Chand | Ajith Pai | Present | completed | resolved | 2020-02-03 | 2020-02-05 | 1.1
11 | login test | testing the login | Akhil | Ajith Pai | Present | completed | resolved | 2020-02-03 | 2020-02-05 | 1.1
12 | Login Edits made | Changed the Login codes for more optimised results | Ajith Pai | Ajith Pai | Present | completed | resolved | 2020-02-05 | 2020-02-08 | 1.2
13 | Agile Doc. | Agile Document filled | Kamal Kandula | Ajith Pai | Present | completed | resolved | 2020-02-03 | 2020-02-08 | N/A
14 | Agile Doc. Edit | Agile Document is edited for making it more precise | Ajith Pai | Ajith Pai | Present | completed | resolved | 2020-02-08 | 2020-02-09 | N/A
15 | Front End Work | the project frontend development is started | Sravan | Ajith Pai | Present | incomplete | unresolved | 2020-02-17 | 2020-02-25 | 1.1
16 | Backend Work | the connections for frontend with Backend to be made | Eskala Srekar | Ajith Pai | Present | incomplete | unresolved | 2020-02-20 | 2020-02-25 | 2.1