## Sheet1
Unique ID | User Stories | Particulars (Today's work- Date to be mentioned) | Assignee | Reporter (Scrum Master) | Present / Absent | Status | Resolution | Created | Due | Fix Version/s
1 | Create Git Repositry | adding all members and checking the clone for all the members | Eskala Srekar | Ajith Pai | Present | completed | resolved | 2020-01-16 | 2020-01-17 | N/A
2 | Module workflow | making the workflow plan for the entire project | Ajith Pai | Ajith Pai | Present | completed | resolved | 2020-01-17 | 2020-01-17 | N/A
3 | Database Design | Design and correction of the database to be used for the project | Ajith Pai | Ajith Pai | Present | completed | resolved | 2020-01-18 | 2020-01-19 | N/A
4 | Idea Finalising | Finalising the whole project implementation. | Eskala Srekar | Ajith Pai | Present | completed | resolved | 2020-01-18 | 2020-01-19 | N/A
5 | Firebase account | making the firebase hosting account | Ajith Pai | Ajith Pai | Present | completed | resolved | 2020-01-20 | 2020-01-21 | N/A
6 | Create online url | Making the url id and deploy hello world | Kamal Kandula | Ajith Pai | Present | completed | resolved | 2020-01-22 | 2020-01-23 | N/A
7 | SRS document Completion | to make the SRS document for the project | Kamal Kandula | Ajith Pai | Present | completed | resolved | 2020-01-23 | 2020-01-28 | 1.0.0
8 | SRS document Correction | All the errors, unrelated details and mistakes are corrected | Ajith Pai | Ajith Pai | Present | completed | resolved | 2020-01-28 | 2020-01-30 | 1.1.0
9 | Login mangament with OTP | The login management is made with Firebase | Kamal Kandula | Ajith Pai | Present | completed | resolved | 2020-01-30 | 2020-02-03 | 1.2.1
10 | login test | testing the login | Prem Chand | Ajith Pai | Present | completed | resolved | 2020-02-03 | 2020-02-05 | 1.2.1
11 | login test | testing the login | Akhil | Ajith Pai | Present | completed | resolved | 2020-02-03 | 2020-02-05 | 1.2.1
12 | Login Edits made | Changed the Login codes for more optimised results | Ajith Pai | Ajith Pai | Present | completed | resolved | 2020-02-05 | 2020-02-08 | 2.1.0
13 | Agile Doc. | Agile Document filled | Kamal Kandula | Ajith Pai | Present | completed | resolved | 2020-02-03 | 2020-02-08 | N/A
14 | Agile Doc. Edit | Agile Document is edited for making it more precise | Ajith Pai | Ajith Pai | Present | completed | resolved | 2020-02-08 | 2020-02-09 | N/A
15 | Front End Work | the project frontend development is started | Sravan | Ajith Pai | Present | completed | resolved | 2020-02-17 | 2020-02-25 | 2.2.0
16 | Backend Work | the connections for frontend with Backend to be made | Eskala Srekar | Ajith Pai | Present | completed | resolved | 2020-02-20 | 2020-02-25 | 2.1
17 | Image Upload | The Image put by user must be stored to database | Eskala Srekar | Ajith Pai | Present | completed | resolved | 2020-03-03 | 2020-03-08 | N/A
18 | Lockdown Phase | Due to Pandemic there was few days gap to communicate. | whole team | Ajith Pai | Absent | N/A | N/A | 2020-03-14 | 2020-04-07 | N/A
19 | KYC Upload | The KYC Image put by user must be stored to database | Eskala Srekar | Ajith Pai | Present | completed | resolved | 2020-04-07 | 2020-04-14 | 2.3.0
20 | UI glicthes fixes | There were few changes in UI | Sravan | Ajith Pai | Present | completed | resolved | 2020-04-10 | 2020-04-14 | 2.3.1
21 | Admin Profile | Creating Admin role and creating dashboard | Sravan | Ajith Pai | Present | completed | resolved | 2020-04-15 | 2020-04-20 | 3.1.0
22 | Admin Profile | all Admin functionality work | Eskala Srekar | Ajith Pai | Present | completed | resolved | 2020-04-21 | 2020-04-25 | 3.2.0
23 | Admin Profile | all Admin functionality work UI | Sravan | Ajith Pai | Present | completed | resolved | 2020-04-22 | 2020-04-24 | 3.2.1
24 | Wallet | In app Wallet making UI | Sravan | Ajith Pai | Present | completed | resolved | 2020-04-25 | 2020-04-30 | 3.3.0
25 | Wallet | In app Wallet Backend | Eskala Srekar | Ajith Pai | Present | completed | resolved | 2020-05-01 | 2020-05-07 | 4.1.0
26 | Add Cart/Checkout | User profile working completion UI | Sravan | Ajith Pai | Present | completed | resolved | 2020-05-08 | 2020-05-15 | 5.1.0
27 | logout/ Update Profile | Final working of the module | Eskala Srekar | Ajith Pai | Present | completed | resolved | 2020-05-09 | 2020-05-16 | 5.1.1
28 | logout/ Update Profile | Final working of the module | Kamal Kandula | Ajith Pai | Present | completed | resolved | 2020-05-10 | 2020-05-17 | 5.2.0
29 | Testing | Complete Application testing | Premchand/Akhil | Ajith Pai | Present | completed | resolved | 2020-05-17 | 2020-05-25 | 5.3.1
30 | Test error Fix | Fixing all the errors discovered | Kamal Kandula | Ajith Pai | Present | completed | resolved | 2020-05-25 | 2020-05-26 | 5.3.2
31 | Final Testing | Final debugging, testing and glitches fixes | Premchand/Akhil | Ajith Pai | Present | completed | resolved | 2020-05-26 | 2020-05-28 | 5.3.3
32 | Project delivery | Final Deployment of the project | Ajith Pai | Ajith Pai | Present | completed | resolved | 2020-05-29 | 2020-06-10 | 5.4.0